## BBRA
4a. Broad Brush Risk Register - Package 2A + 2B |  | NWG PSC Risk
Copy the matching columns from the PMP Risk table into the table below. Note that the Overall Risk Rating is an automatic calculation - do not copy anything into this field. Risks (and any arising issues) are reviewed on a regular basis by the Project Manager. This is to ensure that they are monitored and actioned appropriately, and so any new risks can be captured below:
Risk # | Description of Risk Event This is a specific description of what could happen that would threaten the success of the project. It must address who, what, where, when, why and how the risk could occur – in order to be able to be controlled effectively | Consequences Using the number scale below rate the consequence of each risk on the project if it occurred: Negligible - a very small delay (1 day) and/or minor cost increase (<$10,000) is anticipated Minor - some delay (2-3 days) and/or minor cost increase ($10,000 to $100,00) is anticipated Moderate - key parts of the project will be delayed more than a week and/or a significant cost increase ($100,000 to $500,000) is anticipated Major - key parts of the project will be delayed more than a month and/or a serious cost increase ($500,000 to $1,000,000) is anticipated Severe - the project will completely stop and/or a major cost increase (>$1,000,000) is anticipated | Likelihood (note - likelihood of Risk event with that consequence rating occurring) Using the number scale below rate the likelihood of each risk occurring Rare Unlikely Possible Likely Almost Certain | Overall Risk Rating This field is automatically calculated (Likelihood x Consequences) - there is no need to update this field. The closer the number is to 1, the graver the risk to the project | Mitigation Actions Describe what steps will be taken to reduce the likelihood of this risk occurring | Contingency Plan / Control Measure Recommended for risks with an risk rating > 0.3. What steps have been taken to reduce the impact on the project if this risk occurs | Consequences Using the number scale below rate the consequence of each risk on the project if it occurred: Negligible - a very small delay (1 day) and/or minor cost increase (<$10,000) is anticipated Minor - some delay (2-3 days) and/or minor cost increase ($10,000 to $100,00) is anticipated Moderate - key parts of the project will be delayed more than a week and/or a significant cost increase ($100,000 to $500,000) is anticipated Major - key parts of the project will be delayed more than a month and/or a serious cost increase ($500,000 to $1,000,000) is anticipated Severe - the project will completely stop and/or a major cost increase (>$1,000,000) is anticipated " | Residual Likelihood (note - likelihood of Risk event with that consequence rating occurring) Using the number scale below rate the likelihood of each risk occurring Rare Unlikely Possible Likely Almost Certain | Overall Risk Rating This field is automatically calculated (Likelihood x Consequences) - there is no need to update this field. The closer the number is to 1, the graver the risk to the project | Responsible Owner Who is responsible for controlling this risk to ensure it does not happen? | Status Is the risk current (open) or has it been closed off? | Comments | Package 2A Regional Recovery Partnerships Fund | Package 2B Safe and Secure
T2-NWG Financial Risk | Inadequate Stakeholder Engagement | Major | Unlikely | High | Stakeholders identified in PMP, Establishment of Working Groups with relevant Stakeholders, Funding parameters understood, Engagement with PSC Engineering and Ops | PMO Support | Major | Possible | Medium | PSO | OPEN | NWG Risk - Updated 22.01.24, No Updated - 03.04.24 | Y | Y
T2-NWG Financial Risk | Co-commitments being progressed simultaneously | Major | Likely | High | Stakeholders identified in PMP, Establishment of Working Group with relevant Stakeholders, Robust discussion to comprehensively understand requirements/ timing/ progress/ status of co-commitments, Funding parameters understood, | PMO Support | Major | Possible | Medium | PMO | OPEN | NWG Risk - Updated 22.01.24, No Updated - 03.04.24 | Y | Y
| Inadequate Designs (due to background studies) | Major | Unlikely | High | Specialist Consultant(s) engaged to develop background studies Peer Reviews by Independent Specialists, alignment/ confirmation designs reflect background studies Stakeholders have input into designs (CENTROC Councils, Ops) Working Group input PMO Oversight | Contractor Review + PMO Support | Major | Rare | Medium | PM | OPEN | Noted the requirement for D&C under Funding Agreement. Risk to remain Feb23 | Y | Y
T5-Technical Risks | Inadequate Designs (Design requirements) | Major | Unlikely | High | Specialist Consultant(s) engaged to develop Detail Designs Peer Reviews by Independent Specialists Stakeholders have input into designs (CENTROC Councils, Ops) Working Group input PMO Oversight | Contractor Review + PMO Support | Major | Rare | Medium | PM | OPEN | NWG Risk - Updated 22.01.24, No Updated - 03.04.24 | Y | Y
| Unknown Agency Requirements and Delayed / Non Approvals | Major | Unlikely | High | Specialist Consultant(s) engaged to develop Design and complete Document updates Peer Reviews by Independent Specialists PMO Oversight Early / Regular Consultation with Authorities. | Contractor Review + PMO Support | Major | Rare | Medium | PM | OPEN | No Updates - 03.04.24 | Y | Y
| Limited Relevant Experience of Consultants / Contractor(s) / Subcontractors | Major | Unlikely | High | Quotation / Tender Evaluation Process to Weight Relevant Experience Highly. Panel of experts, DPI involvement, approval process, peer review | PMO Support | Major | Rare | Medium | PM | OPEN | No Updates - 03.04.24 | Y | Y
| HSECQ Incident - Contractor Related | Major | Unlikely | High | Contractor(s) to be escorted by PSC HSECQ during all site visits | PMO Support | Major | Rare | Medium | PSC | OPEN | No Updates - 03.04.24 | Y | Y
| Project Deliverables NOT Fit-for-Purpose | Major | Unlikely | High | Parameters developed and understood by Contractor Regular progress updates to confirm direction Stakeholder input into feedback/ designs Contractor(s) to Comply with ALL Contract Requirements | PMO Support | Major | Rare | Medium | PMO | OPEN | Briefing Meeting/ Kick off meeting re-enforce deliverables are for BCD purposes. Risk to remain unchanged | Y | Y
| Deliberables not completed in timely manner (Deadline for submission closes) | Severe | Possible | Very High | Timeframe for work and application developed and understood by Designer/ Contractor Contractor clarifications closed out ASAP Associated works proceeding when possible wthout delays EoT process understood | PMO Support | Severe | Unlikely | High | PSC | CLOSED | Current Milestones: Milestone 1 - Package 1 Upon review of Draft Business Case Report 26/02/2021 Milestone 2 - Package 1 Upon review of Final Business Case Report 26/03/2021 Milestone 3 - Package 1 Final Report 30/04/2021 Milestone 1 - Package 2 Upon review of Draft Business Case Report 30/04/2020 Milestone 2 - Package 2 Upon review of Final Business Case Report 28/05/2020 Milestone 3 - Package 2 Final Report 25/06/2021 Lachlan Duplication Pipeline (Package 1) the CENTROC Water Grid (Package 2) | Y | Y
| Deliverables not completed in timely manner because consultants cannot meet due to COVID-19 (Deadline for submission closes) | Major | Unlikely | High | Timeframe for work and application developed and understood by Designer/ Contractor Contractor clarifications closed out ASAP Associated works proceeding when possible without delays Workshops and Meetings being progressed online (MS Teams, Teleconference, Skype). | PMO Support | Major | Rare | Medium | PSC | OPEN | No Updates - 03.04.24 | Y | Y
T5-Technical Risks | Demand not fully understood IWCM not completed in time to support BCD | Moderate | Almost Certain | High | Demand analysis is well advanced Progress IWCM in parallel to Safe and Secure BCD, noting that Specialist Studies to support IWCM demand forecasts may not be complete when BC is completed | PSC (AF) | Moderate | Possible | Medium | PSC | OPEN | Mini IWCM/ IWCM update progressing GHD groundwater update progressing, - NWG Updated Risk 22.01.24, NO update for 03.04.24 | Y | Y
T2-NWG Financial Risk | Project Funding Shortfall - Grant Funding | Severe | Possible | Very High | Funding Agreement + Obligations Understood / Managed, Clear Process of Approvals, Early Consultation, Clarifications, Variation Management, Contingency Management, Funding expectations understood (NPM contribution) EoT process understood Potential to review construction budget after tender with Funding Authority | PSC (AF) | Severe | Likely | Very High | GM | OPEN | NPM funding agreement letter obtained / yet to be confirmed / Discussion still in progress with other funding bodies (Feb23), 01.12.23 - Upgraded comments, Very High Risk to PSC - NWG update risk 03.04.24 | Y | Y
| Non-compliance with PSC Policies & Procedures | Severe | Unlikely | High | PSC Policies & Procedures Understood / Managed, Documented Understanding, Consultant / Contractor Mobilisation Process, Utilised Consultant / Contractor Plans, SPE + HSECQ Compliance Supervisor (full time role). | PMO Support | Severe | Rare | Medium | PM | OPEN | No Updates - 03.04.24 | Y | Y
| Non-compliant Risk &/or Management of Change | Severe | Unlikely | High | PSC PIMP Risk & Change Management Processes Implemented / Maintained, Engagement of Senior Management and Staff. | PMO Support | Severe | Rare | Medium | PM | OPEN | No Updates - 03.04.24 | Y | Y
T2-NWG Financial Risk | Project Funding Shortfall - Cost Escalation - Inflation | Major | Possible | Very High | Funding Agreement + Obligations Understood / Managed, Clear Process of Approvals, Early Consultation, Clarifications, Variation Management, Contingency Management, Funding expectations understood (NPM contribution) EoT process understood | PMO Support | Major | Possible | Very High | GM | OPEN | Cost escalation / inflation contributing to Project shortfalls across all RRP and S&S work fronts, 01.12.23 - Upgraded comments, Very High Risk to PSC - NWG Risk Updated - 3.04.24 | Y | Y
T2-NWG Financial Risk | Project Cashflow Maintained | Major | Poissble | High | Project Cashflow Agreed / Managed + Consultation with Finance Department. | PMO Support | Major | Rare | Medium | PM | OPEN | NWG Risk - Updated 22.01.24, No updated - 03.04.24 | Y | Y
T3-Social Risks | Inadequate Community Engagement | Major | Possible | Very High | Stakeholder Consultation Strategy Implemented + Regular Communication, PSC Comms Officer Lead, SPE + HSECQ Compliance Supervisor (full time role) - ongoing. Community reps review of Comms plan. Letter box drops, door knocking, social media updates. Property Matrix development and maintenance | Comms Officer | Moderate | Unlikely | High | PSO | OPEN | PSC/PMO assistance during recent floods have been noted. PSC Ongoing comms manager included in all upcoming engagement(s). 01.12.23 - UpGraded to High, with recent stakeholder engagements, Risk remains, NWG - Residual Update ( Poissible to Unlikely - 03.04.24 | Y | Y
| Interface with existing water transfer infrastructure to Parkes during Construction and Commissioning | Severe | Possible | Very High | Existing Operations Maintained, Water Consumption Understood, effective regular communications with Operations. Time of year (winter with low demand), High dam levels (not drawing from River), Bore infrastructure in good condition (no downtime). Expectation setting with NPM (potential for low demand for short period) Confirm 'wet season' for Parkes/ discharges from Wyangla dam, potential to draw out construction period Cut over and Commissioning Strategy to be developed and implemented | Existing Operations Maintained - Project Delay | Severe | Unlikely | High | MNR | OPEN | Interface agreements, Survey, Intra mapping, detailed design - Unchaged 03.04.24 | Y | Y | Maybe drop Likelyhood to Rare, has not happened in past…
| Inadequate Project Management / Supervision | Major | Unlikely | High | PSC PMBoK processes implemented, PMO Established, incl. PM + SPE + PSO, future + CM + Survey + executive oversight implemented. | Increased Surveillance | Major | Rare | Medium | PM | OPEN | No Updates - 03.04.24 | Y | Y
| Inadequate Construction Management | Severe | Unlikely | High | PSC PMBoK processes implemented, PMO Established, incl. PM + SPE + PSO, future + CM + Survey + Specialist Consultants + Tools & Equipment, HSECQ Compliance Supervisor(s) (full time) + executive oversight implemented. | Increased Surveillance | Severe | Rare | Medium | PM | OPEN | No Updates - 03.04.24 | Y | Y
| Inadequate Public Health / Safety | Severe | Unlikely | High | Safety in Design, WHS Act compliance during construction to minimise risks. PSC / Contractor to Implement Approved Construction Management Plans + Equipment FAT / SAT / Commissioning / Verification / Validation plans. DLP Managed. | Increased Surveillance - Construction + O&M, Retain Existing Plant Operations Until Plant is Validated | Moderate | Rare | Medium | MNR | OPEN | No Updates - 03.04.24 | Y | Y
T5-Technical Risks | Inadequate P&E / Design / Tender / Contract Documentation | Severe | Possible | High | Specialist Consultant(s) engaged to develop the Planning & Environmental + Design + Tender / Contract Documentation + Peer Reviews by Independent Specialists. PMO Oversight, incl. SPE. Safety in Design practices adopted - BBRA / CHAIR / HAZOP / HACCP / Design Review Processes | Contractor Review + PMO Support | Severe | possible | Medium | MNR | OPEN | NWG Risk - Updated 22.01.24 | Y | Y
| Site Selected is NOT Suitable / Adequate - "Energy Efficient" + "Future Proofed" - CAPEX vs OPEX Value Management | Major | Unlikely | High | Background studies / site monitoring utilised for Design. Site requirements to be known - investigations if required. Specialist Consultant(s) to develop the Design Documentation. Site requirements to be known - investigations if required. Specialist Consultant(s) to develop the P&E + Design Documentation. Peer Review + Sustainable Reviews throughout project deliver process. Formal Site Selection process to be completed, incl. Council Approval. | GM + Risk Committee Oversight | Major | Rare | Medium | MNR | OPEN | OPEX to include consideration for Depreciation. Comment remains. Risk remains | Y | Y
| Non-compliance with Statutory Requirements under the EPA Act 1979 - DPIE Involvement / Approval | Major | Likely | Very High | Authority Comments Obtained / Incorporated - Early / Ongoing Consultation with EPA. Site requirements to be known - investigations if required. Specialist Consultant(s) engaged to develop the Planning & Environmental + Design + Tender / Contract Documentation + Peer Reviews by Independent Specialists. PMO Oversight, incl. SPE. Early / Regular Consultation with Authorities. PSC / Contractor to Implement Approved Construction Management Plans + SAT / Commissioning / Training / Verification / Validation plans. DLP Managed. Environmental to be considered in tender evaluation | Contractor Review + PMO Support | Major | Unlikely | High | MNR | closed | Noted - This line item has been split for better reference to the EPA ACT and code. See line item 32 & 33 | Y | Y
T6-Enviromental Risks | Non-compliance with Statutory Requirements under the Environmental Planning & Assessment Act 1979 (EP&A Act), Environmental Planning and Assessment Regulation 2021 (EP&A Regulation 2021) and the State Environmental Planning Policy (Transport and Infrastructure) 2021 | Major | Likely | Very High | Authority Comments Obtained / Incorporated - Early / Site requirements to be known - investigations if required. Specialist Consultant(s) engaged to develop the Planning & Environmental + Design + Tender / Contract Documentation + Peer Reviews by Independent Specialists. PMO Oversight, incl. SPE. Early / Regular Consultation with Authorities. PSC / Contractor to Implement Approved Construction Management Plans + SAT / Commissioning / Training / Verification / Validation plans. DLP Managed. | Contractor Review + PMO Support | Major | Unlikely | High | MNR | OPEN | Mitigation action, development of the REF No licencing anticipated (see further details below), Risk remaining of pollution of waters from sediment release during construction Consultation with communities identified as high priority given the nature of the site Assessment of cumulative impacts should occur as part of developing the REF Consequence to be downgraded No Updates 01.12.23, NWG Risks - Residual Update ( Poissible to Unlikely - 03.04.24
| Non-compliance with Statutory Requirements under the Protection of the Environment and Operations Act 1997 (POEO Act) | Major | Likely |  | Authority Comments Obtained / Incorporated - Early / Site requirements to be known - investigations if required. Specialist Consultant(s) engaged to develop the Planning & Environmental + Design + Tender / Contract Documentation + Peer Reviews by Independent Specialists. PMO Oversight, incl. SPE. Early / Regular Consultation with Authorities. PSC / Contractor to Implement Approved Construction Management Plans + SAT / Commissioning / Training / Verification / Validation plans. DLP Managed. | Contractor Review + PMO Support | Major | Unlikely | High | MNR | OPEN | Based on current design, license from EPA not anticipated as project is not expected to generate discharge of pollution to the environment as part of operations. Still need to be aware of potential breaches from discharge of sediment into waterways during construction. ERSED measures to be implemented to mitigate risks
T6-Enviromental Risks | Unknown Factor in Increased Water Demand | Severe | Unlikely | High | New IWCM to be prepared prior to project completion - ensure consistency. IWCM Plan Understood, incl. Regional Requirements Understood / Managed. Parkes Projection Requirements Understood / Managed. Specialist Consultant(s) engaged to develop the Planning & Environmental + Design + Tender / Contract Documentation + Peer Reviews by Independent Specialists. PMO Oversight, incl. SPE. WTP designed for future expansion. | Contractor Review + PMO Support | Severe | Rare | Medium | Dir. Inf. | OPEN | NWG - Updated 22.01.24, No updates - 03.04.24 | Y | Y
| Value for Money + Technology / Process Risk Management | Severe | Unlikely | High | Procurement Strategy to be developed - explore all options (via risk assessment), incl. DD&C (EPCM by PSC with E to 75% prior to DD&C), DD&C+O&M (O&M only for the DLP), Construct only (EPCM by PSC with E to 100% prior to Construct), LEAN (EPCM by PSC + trade packages) | Contractor Review + PMO Support | Severe | Rare | Medium | MNR | OPEN | No Updates - 03.04.24 | Y | Y
| Limited Relevant Experience of Consultants / Contractor(s) / Subcontractors | Major | Unlikely | High | Quotation / Tender Evaluation Process to Weight Relevant Experience Highly. Panel of experts, approval process, peer review, validated equipment, stakeholder input | Increased Surveillance | Major | Rare | Medium | MNR | OPEN | No Updates - 03.04.24 | Y | Y
T2-NWG Financial Risk | Form of Contract - Financial Capacity of Consultants / Contractor(s) | Severe | Possible | Very High | Quotation / Tender Evaluation Process to Confirm Financial Capacity of Consultants / Contractor(s), incl. specialist Assessor to audit Accounts as necessary. Noted that some Contractors are currently having financial issues (e.g. FB closed) | Payment Management + Project Security in the form of Unconditional Undertakings | Severe | unlikely | High | PM | OPEN | Residual Update ( Poissible to Unlikely - 03.04.24 | Y | Y
| Form of Contract - Contractor Payments to Subcontractors | Severe | Unlikely | High | Contractor(s) to provide Statutory Declarations confirming Subcontractor Payments with each Progress Claim - PSC to Validate, View Subcontractor payments, schedules and status, Relationship building techniques with the Subcontractor (transparent communication). | Payment Management + Project Security + Security of Payment | Severe | Rare | Medium | PM | OPEN | No Updates - 03.04.24 | Y | Y
T2-NWG Financial Risk | Contract Approval - Delays | Major | Likely | Very High | Council Approval Process Understood / Managed, Funding Authorities updated. Communications Plan for Councillors involving workshop opportunities. | PMO Support | Major | unlikely | High | MNR | OPEN | Residual Update ( Poissible to Unlikely - 03.04.24 | Y | Y
| HSECQ Incident - Contractor Related | Severe | Possible | Very High | Tender Evaluation Processes to Weight HSECQ Performance Highly + Contractor(s) to Comply with ALL Contract Requirements + PSC Surveillance, incl. Monitoring Site Activities, SPE + HSECQ Compliance Supervisor employed full time - site surveillance. | Increased Surveillance | Severe | Rare | Medium | PSC | OPEN | No Updates - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
| HSECQ Incident - Contractor Related - Maintenance | Severe | Possible | Very High | Tender Evaluation Process to Weight HSEQ Performance Highly + PSC to Review Proposed Maintenance Plan + Contractor(s) to Comply with ALL Contract Requirements + PSC Surveillance through Construction Cam + SPE + HSECQ Compliance Supervisor. | Increased Surveillance | Severe | Rare | Medium | PSC | OPEN | No Updates - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
| Community Incident - Contractor Related | Severe | Possible | Very High | Tender Evaluation Process to Weight Community Performance Highly + Contractor(s) to Comply with ALL Contract Requirements + PSC Surveillance. | Non-compliant Personnel Remove from the Project + Increased Surveillance | Severe | Rare | Medium | PSC | OPEN | No Updates - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
| Interaction with PSC Operations - Incident | Major | Unlikely | High | Contractor advised of PSC Operations Access Requirements + PSC Operations Site Induction into Project Area. SPE + HSECQ Compliance Supervisor (full time). | PMO Support | Major | Rare | Medium | PCS | OPEN | No Updates - 03.04.24 | Y | Y
| Tender Mishandling / Procurement Challenge | Major | Unlikely | High | Oversight by Probity Advisor, provision of comprehensive procurement / probity briefing by Probity Advisor to Tender Team, comprehensive Evaluation Methodology, ensuring consistency between Evaluation Methodology and Conditions of Tender, ensuring Process complies with relevant tendering legislation and policies | PMO/ L&P Advisor | Major | Rare | Medium | PSC | OPEN | No Updates - 03.04.24 | Y | Y
T6-Enviromental Risks | Environmental Conditions Affecting Persons | Major | Possible | Very High | Tender Evaluation Process to Weight HSEQ Performance Highly + Contractor(s) to Comply with ALL Contract Requirements, Contractor to Implement Approved Construction Environmental Management Plan (CEMP) + PSC Surveillance. | Increased Surveillance | Major | Likely | Very High | PSC | OPEN | No Updates - Unchanged 04.12.23, NWG Risk - Updated 03.04.24 | Y | Y | Maybe drop Likelyhood to Rare, has not happened in past…
| Non-compliance with POEO Act - EPA Involvement | Major | Likely | Very High | Authority Comments Obtained / Incorporated - Early / Ongoing Consultation with EPA. Site requirements to be known - investigations if required. Specialist Consultant(s) engaged to develop the Planning & Environmental + Design + Tender / Contract Documentation + Peer Reviews by Independent Specialists. PMO Oversight, incl. SPE. Early / Regular Consultation with Authorities. PSC / Contractor to Implement Approved Construction Management Plans + SAT / Commissioning / Training / Verification / Validation plans. DLP Managed. Environmental to be considered in tender evaluation | Contractor Review + PMO Support | Major | Possible | High | MNR | closed | Flood impacts driving risk / Methodology / scoping the works, Risk and likely hood upgraded to possible/High, NOTED THIS RISK HAS BEEN EXPANDED IN LINE ITEM-47 / 48 / 49 / 50 & 51 | Y | Y
T6-Enviromental Risks | Non-compliance with Statutory Requirements under the Protection of the Environment and Operations Act 1997 (POEO Act) | Major | Likely | Very High | Authority Comments Obtained / Incorporated - Early / Site requirements to be known - investigations if required. Specialist Consultant(s) engaged to develop the Planning & Environmental + Design + Tender / Contract Documentation + Peer Reviews by Independent Specialists. PMO Oversight, incl. SPE. Early / Regular Consultation with Authorities. PSC / Contractor to Implement Approved Construction Management Plans + SAT / Commissioning / Training / Verification / Validation plans. DLP Managed. | Contractor Review + PMO Support | Major | Unlikely | High | MNR | OPEN | Based on current design, license from EPA not anticipated as project is not expected to generate discharge of pollution to the environment as part of operations. Still need to be aware of potential breaches from discharge of sediment into waterways during construction. ERSED measures to be implemented to mitigate risks - Residual Update ( Poissible to Unlikely - 03.04.24
T6-Enviromental Risks | Non-compliance with Statutory Requirements under the Environment Protection and Biodiversity Conservation Act 1999 (EPBC Act), Biodiversity Conservation Act 2016 (BC Act) and Fisheries Management Act 1994 | Major | Likely | Very High | Authority Comments Obtained / Incorporated - Early / Site requirements to be known - investigations if required. Specialist Consultant(s) engaged to develop the Planning & Environmental + Design + Tender / Contract Documentation + Peer Reviews by Independent Specialists. PMO Oversight, incl. SPE. Early / Regular Consultation with Authorities. PSC / Contractor to Implement Approved Construction Management Plans + SAT / Commissioning / Training / Verification / Validation plans. DLP Managed. | Contractor Review + PMO Support | Major | unlikely | High | MNR | OPEN | The site and proposed impact area are of low constraint regarding ecological features. The proposed impact area is mostly non-native vegetation (with a large number of planted non-native peppercorn trees, several of which were observed to contain hollows), managed recreational sporting facilities and residential and urban areas. Effort has been made to position the detention basin such that potential ecological impacts have been avoided. It was noted during the site assessment that planted trees throughout the site (which do provide potential habitat for native species and are of value for their aesthetic and shading value on the site) will be retained. An REF can be prepared without a standalone Flora and Fauna Assessment (assuming the concept design and site layout doesn’t change from that shown during the site visit). No waterways impacted therefore unlikely to require Fisheries Permit.Residual Update ( Poissible to Unlikely - 03.04.24
T6-Enviromental Risks | Non-compliance with Statutory Requirements under the National Parks and Wildlife Act 1974 (NPW Act) and Heritage Act 1997 | Major | Likely | Very High | Authority Comments Obtained / Incorporated - Early / Site requirements to be known - investigations if required. Specialist Consultant(s) engaged to develop the Planning & Environmental + Design + Tender / Contract Documentation + Peer Reviews by Independent Specialists. PMO Oversight, incl. SPE. Early / Regular Consultation with Authorities. PSC / Contractor to Implement Approved Construction Management Plans + SAT / Commissioning / Training / Verification / Validation plans. DLP Managed. | Contractor Review + PMO Support | Major | Unlikely | High | MNR | OPEN | Residual Update ( Poissible to Unlikely - 03.04.24
T6-Enviromental Risks | Non-compliance with Statutory Requirements under the Water Management Act 2000 (WM Act) | Major | Likely | Very High | Authority Comments Obtained / Incorporated - Early / Site requirements to be known - investigations if required. Specialist Consultant(s) engaged to develop the Planning & Environmental + Design + Tender / Contract Documentation + Peer Reviews by Independent Specialists. PMO Oversight, incl. SPE. Early / Regular Consultation with Authorities. PSC / Contractor to Implement Approved Construction Management Plans + SAT / Commissioning / Training / Verification / Validation plans. DLP Managed. | Contractor Review + PMO Support | Major | Unlikely | High | MNR | OPEN | No licensing anticipated for the project. License may be required for any future upgrades where stored water is used for irrigation purposes on neighbouring playing fields. This is currently not within project scope. - Residual Update ( Poissible to Unlikely - 03.04.24
T6-Enviromental Risks | Non-compliance with Statutory Requirements Crown Land Management Act 2016 (CM Act) | Major | Likely | Very High | Authority Comments Obtained / Incorporated - Early / Site requirements to be known - investigations if required. Specialist Consultant(s) engaged to develop the Planning & Environmental + Design + Tender / Contract Documentation + Peer Reviews by Independent Specialists. PMO Oversight, incl. SPE. Early / Regular Consultation with Authorities. PSC / Contractor to Implement Approved Construction Management Plans + SAT / Commissioning / Training / Verification / Validation plans. DLP Managed. | Contractor Review + PMO Support | Major | Unlikely | High | MNR | OPEN | The site has been identified as including areas of Crown Land. The Pioneer Oval, NorthPark's Oval and Spicer Park is an area of Crown Land managed by Parkes Shire Council for the purposes of recreation. Council are in the process of determining if the land use is appropriate and whether a Crown Land License is required for the project. Risk to remain Feb23 - Residual Update ( Poissible to Unlikely - 03.04.24
| Contract Compliance | Major | Possible | Very High | Clear Contract Conditions, Thorough Pre-Tender Briefing, Selection of high quality capable contractor (checking references), ensuring Contract Deliverables are received and thoroughly reviewed and assisting Contractor where potential non-compliance identified, Establishment of AAR | PMO | Major | Unlikely | High | PSC | OPEN | Residual Update ( Poissible to Unlikely - 03.04.24 | Y | Y
| Project Deliverables NOT Fit-for-Purpose | Major | Possible | Very High | Comprehensive P&E / Design / WAE / O&M Documentation + Contractor(s) to Comply with ALL Contract Requirements, Progressive Handover + PSC Surveillance, SPE + HSECQ Compliance Supervisor (full time), Weekly QMS Auditing + FAT + SAT. + Training / Commissioning / DLP Managed, Early involvement of DPI/ Authorities Designs for RRP and S&S are completed in sympathy/ simultaneously | Increased Surveillance | Major | Rare | Medium | PSC | OPEN | No Updates - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
| Contractor Solvency | Major | Possible | Very High | Comprehensive assessment of shortlisted tenderer's solvency prior to award and consideration of alternate contractor should a substitute be needed to finalise the project | PMO | Major | Rare | Medium | PSC | OPEN | No Updates - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
| Non-compliant Operational Readiness Handover | Major | Unlikely | High | Requirements Understood / Managed + Consultation / Plan Agreed & Implemented. Plant FAT / SAT / Training / Commissioning / Verification / Validation plans + WAE / O&M Docs Provided prior to Completion. ORAP developed and being utilised | PMO Support | Major | Rare | Medium | PM | OPEN | No Updates - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
| Conflict of Interest Not Managed | Major | Possible | Very High | Oversight by Probity Advisor, provision of comprehensive procurement / probity briefing by Probity Advisor to Tender Team, declaration of conflicts of interest, comprehensive Evaluation Methodology, ensuring consistency between Evaluation Methodology and Conditions of Tender, ensuring Process | PMO | Major | Rare | Medium | PSC | OPEN | No Updates - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
T1-Reputational Risk | Reputational Risk to other Infrastructure Assets owned by Stakeholder | Major | Possible | Very High | PIMP processes implemented, executive oversight implemented, PMO established, involvement of personnel responsible for other Infrastructure Assets (Ops), Stakeholder engagement/ Comms being progressed, Media management | PMO Support | Major | Unlikely | High | MNR | OPEN | Residual Update ( Poissible to Unlikely - 03.04.24 | Y | Y
| Remote Site Access Prior / During / Completion | Major | Unlikely | High | PSC to review / upgrade prior to the commencement of works, Contractor(s) to complete a dilapidation survey & maintain the roads, PSC to assess at completion of the project, Contractor(s) DLP works if necessary. | Increased Surveillance | Major | Rare | Medium | PCS | OPEN | No Updates - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
| Operator Skills and Performance | Major | Unlikely | High | Requirements Understood / Managed + Consultation / Plan Agreed & Implemented. Training / Skills Matrix Developed. Plant FAT / SAT / Training / Commissioning / Verification / Validation plans + WAE / O&M Docs Provided prior to Completion. | PMO Support | Major | Rare | Medium | PM | OPEN | No Updates - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
| Lack of Optimising of Operational Costs - "Carbon Smart" / Sustainable Principles | Severe | Unlikely | High | Specialist Consultant(s) / Operator input required during DD phase / throughout project delivery to ensure Optimising of Operational Costs - "Carbon Smart" / Sustainable Principles are incorporated / achieved | PMO Support | Severe | Rare | Medium | MNR | OPEN | No Updates - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
| Long Lead Items Impacting Timely Delivery of Project | Major | Likely | Very High | Design, supplier and technology selection process is using equipment manufacturer and lead times into consideration during evaluation. Project Schedule implemented & maintained, incl. Procurement / Long Lead aspects / impacts. Industry RFI processes to better understand market capacity/ capability | Contractor Review + PMO Support | Major | Unlikely | High | PM | OPEN | Noted that Essential Energy power upgrades, potential to progress concurrently with BCD.Risk to remain.Feb23, Review Mar.23- Residual Update ( Poissible to Unlikely - 03.04.24 | Y | Y
| Inclement Weather Impacts - Project Delays | Major | Likely | Very High | Monitor long and short term weather forecast and take appropriate action in form of schedule changes, site preparation and other suitable control measures. Factor in Contingency/ Float. EoT process understood | Contract Acceleration + PMO Support | Major | Likely | Very High | PMO | OPEN | Aug22 - Dec2022 - flooding in Lachlan precinct area( Forbes ), review of the imapcts driving project delays - risk to remain Feb23 / Mar23, - Residual Update ( Poissible to Unlikely - 03.04.24 | Y | Y
| Engagement / Delivery Format unsuitable. Contractual Arrangements and cost of Ownership | Major | Possible | Very High | Early Engagement of Contract Specialist and long term cost of ownership projections / calculations to determine actual cost. | Contractor Review + PMO Support | Major | Rare | Medium | PM | OPEN | Unchanged, Risk Remains - 01.12.23, No update 03.04.24 | Y | Y
| Contractors NOT complying with Ethical Business Standards and Practices in Procurement Activities | Major | Unlikely | High | PSC Policies & Procedures Understood / Managed, Documented Understanding, Consultant / Contractor Procurement, Engagement & Mobilisation Process Managed, Utilised Consultant / Contractor Plans, SPE + HSECQ Compliance Supervisor (full time role). | PMO Support | Major | Rare | Medium | PM | OPEN | No Updates - 03.04.24 | Y | Y
| In-effective Procurement Process - Selective Tender Process, incl. EOI with Priced & Non-price Criteria Developed - DD&C Fixed Lump Sum Tenders | Major | Unlikely | High | Procurement Strategy to be developed - explore all options (via NPV & risk assessment), incl. DD&C (EPCM by PSC with E to 75% prior to DD&C), DD&C+O&M (O&M only for the DLP), Construct only (EPCM by PSC with E to 100% prior to Construct), LEAN (EPCM by PSC + trade packages) | Contractor Review + PMO Support | Major | Rare | Medium | MNR | OPEN | No Updates - 03.04.24 | Y | Y
| Contractors Unable to Comply with Local Benefit and Local Participation Engagement | Major | Unlikely | High | PSC Policies & Procedures Understood / Managed, Documented Understanding, Consultant / Contractor Procurement, Engagement & Mobilisation Process Managed, Utilised Consultant / Contractor Plans, SPE + HSECQ Compliance Supervisor (full time role). | PMO Support | Major | Rare | Medium | PM | OPEN | No Updates - 03.04.24 | Y | Y
| Contractors NOT complying with Ethical Business Standards and Practices in Procurement Activities | Major | Unlikely | High | PSC Policies & Procedures Understood / Managed, Documented Understanding, Consultant / Contractor Procurement, Engagement & Mobilisation Process Managed, Utilised Consultant / Contractor Plans, SPE + HSECQ Compliance Supervisor | Tender Committee + PMO Support | Major | Rare | Medium | PMO | OPEN | No Updates - 03.04.24 | Y | Y
| In-effective Procurement Process - Tender Process, incl. RFI with Priced & Non-price Criteria Developed - DD&C Fixed Lump Sum Tenders | Major | Unlikely | High | Procurement plan to incl. Probity Plan prepared by the Facilitator. Procurement Strategy developed - explore all options (via NPV & risk assessment). DD&C (EPCM by PSC with E to Preliminary prior to DD&C) + DD&C+O&M (O&M only for the DLP + 12months) | Tender Committee + PMO Support | Major | Rare | Medium | PMO | OPEN | No Updates - 03.04.24 | Y | Y
| Increase Cost + Potential for Delays if PSC Progress Associated Infrastructure Packages | Major | Possible | Very High | PSC to review internal capacity and only progress associated infrastructure packages that WILL BE completed on time / on budget. All PSC associated infrastructure works teams to regularly (weekly) coordinate with PMO. | Increased Surveillance | Major | unlikely | High | Dir. Inf. | OPEN | Flood impacts driving risk / Methodology / scoping the works, Review of impending costing review in feb23, Residual Update ( Poissible to Unlikely - 03.04.24 | Y | Y
| Increased Risk with Battery Limits / Contractor Interfaces/ incl. PSC Associated Infrastructure Works | Major | Possible | Very High | Interface Working Groups established. Regular (Weekly) Consultant / Contractor Interface Coordination Meetings. PMO Supervision to Cover Interfacing Contracts. Interface Matrix to be developed. | Increased Surveillance | Major | Unlikely | High | PMO | OPEN | Unchanged, Risk Remains - No updates risk to remain, Unchanged - 01.12.23, No updates 03.04.24 | Y | Y
| Project Cost & Time Overruns Due to Lack of Resource - All Projects Running Concurrently | Major | Unlikely | High | Balance Local / Regional Content with Cost / Time Constraints. Combine Projects - Resource Levelling. | Contractor Review + PMO Support | Major | Rare | Medium | Dir. Inf. | OPEN | No Updates - 03.04.24 | Y | Y
| Constrained Future Use of Adjacent Properties | Major | Possible | Very High | Review of potential future uses of adjacent properties to be completed - site design to ensure no constraints exist or ensure limitations are known. Site optimisation to be completed. Use of site reservoirs on locations of existing infrastructure Consultation with landholders/ expectation setting | GM + Risk & Steer. Co. Committees Oversight + PMO Support | Major | Rare | Medium | Dir. Inf. | OPEN | Unchanged, Risk Remains - Unchanged 01.12.23, No updates 03.04.24 | Y | Y
| Failure of Existing Water Transfer Infrastructure | Major | Unlikely | High | PSC progressing investigation into existing pipeline condition. Existing water retaining infrastructure maintained by Ops. Spare pipe/ alternative short term solutions available. | MNR | Major | Rare | Medium | PMO | OPEN | No Updates - 03.04.24 | Y | Y
| Project Delays - Insufficient Council Resources - Multiple Major Projects - Critical Drought, BBRF, RRP, S&S | Major | Possible | Very High | Escalate internal delays via Steer.Co. & Risk Review Committee. Proactively coordinate project needs with stakeholders / internal functions. Reduced attention required for most projects when handed to Ops | GM + Risk & Steer. Co. Committees Oversight + PMO Support | Major | Rare | Medium | Dir. Inf. | OPEN | Unchanged, Risk Remains - unchanged 04.12.23, No updates 03.04.24 | Y | Y
| Noise and Vibration Impacts from Construction Activities + Noise and Vibration from Increased Traffic Along Access Roads | Moderate | Likely | High | Control noise generated through control of operating hours, use of AS compliant equipment, ongoing monitoring and adaptive management. Work to be progressed in hours as described in REF. | PMO Support + Contractor Management | Moderate | Unlikely | Medium | PMO | OPEN | No Updates - 03.04.24 | Y | Y
| Surface and Groundwater - Impacts on Water Quality + Impacts on Surface Water Flows (including flood potential) + Impacts on Groundwater Flows | Major | Possible | Very High | Implement mitigation measures designed to minimise risk of pollution to surface and groundwater - contain all spills, conduct vehicle/plant washdown offsite in appropriate bunded area, complete all necessary approvals (NOW, EPA, DPI Fisheries) for design and implementation. Design to minimise impacts to surface and groundwater flows for the long-term. Highlight route and site selection process undertaken to result in avoidance of flood plain of Goobang Creek/ Lachlan River. Install and maintain ERSED controls. | GM + Risk & Steer. Co. Committees + PMO Support + Contractor Management | Major | Unlikeley | High | PMO | OPEN | Flood impacts driving risk / Methodoligy / scoping the works, Risk and likely hood upgraded to Likely/High - Residual Update ( Poissible to Unlikely - 03.04.24 | Y | Y
| Flora and Fauna - Potential Impacts to Threatened Species and Endangered Ecological Communities + Potential Impacts to Remnant Native Vegetation and Wildlife Corridors + Potential Impacts to Aquatic Ecosystem (Goobang Creek) and Groundwater Dependent Ecosystems | Major | Unlikely | High | Route and location designed to avoid removal of native vegetation. Specialist terrestrial and aquatic ecological studies undertaken to categorize species/communities present and guide best practice management actions. Trenching controls e.g. ramps, covering at the end of the work day, inspections. Protocols for injured wildlife or wildlife that is encountered during works. Conducting work in accordance with approvals. Controls for works in/near waterways. Revegetation of disturbed areas. | GM + Risk & Steer. Co. Committees + PMO Support + Contractor Management | Major | Rare | Medium | PMO | OPEN | No Updates - 03.04.24 | Y | Y
| Air Quality - Impacts of Dust from Construction Activities + Impacts of Additional Heavy Traffic Along Unsealed Access Road to Sensitive Receivers + Potential for Airborne Contaminants to Enter Goobang Creek Water. | Major | Unlikely | High | Dust suppression activities undertaken during construction, air quality assessments undertaken prior to and during construction works, adaptive management principles applied. Progressive rehabilitation of disturbed areas. Minimising the area disturbed at any one time. Complaints management. | PMO Support + Contractor Management | Major | Rare | Medium | PMO | OPEN | No Updates - 03.04.24 | Y | Y
| Potential to Impact Aboriginal Heritage | Major | Possible | Very High | AHIMS Register check and specialist heritage studies undertaken prior to final site selection and design/construction activities amended to avoid Aboriginal Heritage artefacts. Local Elders to be inducted to project and advised of works as they progress. Unexpected finds protocol. Progressing AHIP (if required) | PMO Support + Contractor Management | Major | Likely | Medium | PMO | OPEN | Risk to Remain, Updated Rare to Likely, based on recent Jan/Feb field investigation with Parkes - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
| Potential to Impact Non-Aboriginal Heritage | Major | Unlikely | High | AHIMS Register check and specialist heritage studies undertaken prior to final site selection and design/construction activities amended to avoid Heritage artefacts. Unexpected finds protocol. | PMO Support + Contractor Management | Major | Likely | Medium | PMO | OPEN | Risk to Remain, Updated Rare to Likely, based on recent Jan/Feb field investigation with Parkes | Y | Y
| Delay or lack of Emergency Services access and support during emergencies | Major | Possible | Very High | Emergency Services (LEMC) are familiar with major projects. Note LEMC in WHS plans. | PMO Support + Contractor Management | Major | Rare | Medium | PMO | OPEN | Risk Remains - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
| The experience and knowledge of the contractor's project team in delivery of the chosen infrastructure/process | Major | Possible | Very High | Utilise the tender process to obtain a comprehensive understanding of the contractors strengths and weakness and their overall ability to design construct and commission the project. Select the most appropriate contractor out of the tender process and not be focused on the lowest quotation No post tender swap out | PMO Support + Contractor Management | Major | Unlikely | High | PSC/PMO | OPEN | Unchanged, Risk Remains - Residual Update ( Poissible to Unlikely - 03.04.24 | Y | Y
T2-NWG Financial Risk | Delays caused by natural event and govt. funding window closes | Severe | Possible | Very High | Contract covers (force major or natural disaster) so PSC are not exposed to loss of funding EoT process understood, regular updates to contractors, | PMO Support + Contractor Management | Severe | Possible | Very High | Dir. Inf. | OPEN | No Updates - Unchanged 04.12.23, NWG - Updated 03.04.24 | Y | Y
| Critical equipment/ plant/ items constructed that are not compliant to Specs and Standards | Major | Possible | Very High | Stringent QA by Contractor and surveillance by full time PSC HSECQ Supervisor. Ongoing ITP and early Lot Close out | PMO Support + Contractor Management | Major | Rare | Medium | PMO | OPEN | Unchanged, Risk Remains - Unchaged 04.12.23, No update 03.04.24 | Y | Y
| Unexpected geological conditions, such as, fissures, faults, excessive voids, non-uniform foundation, strength of rock. | Major | Unlikely | High | D&C may perform further geotechnical assessments; although ultimately the D&C hold the risk. Consult between the PMO on making sure contract is adequate that regardless of the ground conditions the contract holds the risk. | PMO Support/Consultants | Major | Rare | Medium | PMO/PMO Consultants | OPEN | No Updates - 03.04.24 | Y | Y
| Security during construction (vandals) | Major | Unlikely | High | Establish fence around site. Lock up site after hours. CCTV. Engage security contractor. | Contractor to maintain full time security on site | Major | Unlikely | Medium | Contractor | OPEN | No Updates - 03.04.24 | Y | Y
| Security during operation (terrorism) | Severe | Unlikely | High | Acts of terrorism in remote country towns not likely due to potential impact , CCTV, security, fence, Engage security contractor. | Monitoring risk levels in Parkes | Severe | Rare | Medium | Contractor | OPEN | No Updates - 03.04.24 | Y | Y
| Failure of alarms and monitoring equipment | Major | Unlikely | High | Operational procedures and records for the maintenance of equipment, including the calibration of monitoring equipment, schedules and timelines, responsibilities, resource requirements with alarm systems to indicate when operational target criteria has been exceeded. Monitoring failures should not compromise the system and in some cases at control points, backup equipment to be installed. | PMO, Contractor, PSC | Major | Rare | Medium | PMO | OPEN | No Updates - 03.04.24 | Y | Y
| Inadequate equipment | Major | Possible | Very High | Operational procedures and records for the maintenance of equipment, including the calibration of monitoring equipment, schedules and timelines, responsibilities, resource requirements with alarm systems to indicate when operational target criteria has been exceeded. Monitoring failures should not compromise the system and in some cases at control points, backup equipment to be installed. | PMO, Contractor, PSC | Major | Rare | Medium | PMO | OPEN | Risk Remains - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
| Insufficient Incident and Emergency Response Protocols | Major | Possible | Very High | Potential incidents and emergencies to be defined, and response plans developed and documented in advance of any incident. Plans and procedures should be developed in consultation with relevant regulatory authorities and other key agencies, and should be consistent with existing government emergency response arrangements | PMO, Contractor, PSC | Major | Unlikely | High | PMO | OPEN | Flood impacts driving risk / Methodoligy / scoping the works, Risk and likely hood upgraded to possible/High, jan23 review unchanged. Risk to remian unchanged.Feb23,Residual Update ( Poissible to Unlikely - 03.04.24 | Y | Y
| Increased Economic Viability not acceptable | Major | Possible | Very High | Ensure proposed benefits are real and experienced (e.g. industrial growth, NPM production rates, water restrictions reduced, public perception) | PMO/PSC | Major | Rare | Medium | PMO | OPEN | Risk Remains - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
| Contractor developed spec inadequate to produce fit for purpose product | Major | Possible | Very High | PSC Specification development, PMO/ Ops thorough review of Contractor Specification prior to Execution of Deed, Performance based requirements in Spec, Validated equipment, | PMO, Contractor, PSC | Major | Rare | Medium | PMO | OPEN | Risk Remains - Unchanged 04.12.23,No Updates 03.04.24 | Y | Y
T1-Reputational Risk | Failure of Compulsory acquisition of property, causing delay and reputational impacts | Major | Possible | Very High | Land Owners kept informed as project progresses, Criticality and Benefits of projects made known to Land Owners, Value of land understood (Property Valuation), EIS State planning approval, Utilisation of Public Works Dept to progress EIS, Progressing EIS concurrently with Business Case Approval | MGR | Major | Possible | Very High | Dir. Inf. | OPEN | NWG - Updated 03.04.24 | Y | Y
| Failure of Negotiated acquisition of property | Major | Possible | Very High | Land Owners kept informed of project, Criticality of projects made known to Land Owners, Value of land understood (Property Valuation), | MGR | Major | Rare | Medium | PMO | OPEN | Risk Remains - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
T6-Enviromental Risks | Damage to wetland/ environmentally sensitive area during pipeline construction | Major | Possible | Very High | Contractor aware of environmental significance Construction methodology in sympathy with environmental requirements, Permits obtained, Agency consultation, Contractor adopt appropriate construction methodologies | PMO, Contractor, PSC | Major | Unlikely | High | PMO | OPEN | Flood impacts driving risk / Methodology / scoping the works, Risk and likely hood upgraded to possible/High, jan23 review unchanged. Risk to remain unchanged.Feb23, - Unchaged 04.12.23, Residual Update ( Poissible to Unlikely - 03.04.24 |  | Y
| Incident with existing infrastructure in congested corridors/ areas | Major | Possible | Very High | Design process to identify areas of congestion/ clash and mitigate as much as practical, DBYD during Design and Construction phases, Positive location/ potholing of services PRIOR to construction, Contractor Construction Plan | PMO, Contractor, PSC | Major | Unlikely | High | PMO | OPEN | Risk Remains - Unchanged 04.12.23, No updates 03.04.24 | Y | Y
| An ABC radio journalist picks up a news wire story about a funding announcement for the project. The journalist calls Council’s Mayor and North Parkes Mines and asks each the same questions relating to the value of the project funding and who will benefit from it. Council and NPM provide different responses and the journalist broadcasts a negative story which implies government funding will benefit commercial interests to the detriment of local residents and the environment. | Major | Likely | Very High | 1) Share SEP and risk mgt approach 2) Regular meetings 3) Develop shared messages 4)Media Protocols agreed (CENTROC) Comms to focus on construction of infrastructure aspect (not focus on water security) | PMO, Contractor, PSC | Major | Unlikely | High | PMO | Closed | Recommended this Risk be reworkded and reclassified for Feb23 Review. | N | N
| As part of the funding review process before signing the funding deed, state government agencies review the cost benefit analysis of the projects and conclude that the funding does not fit the parameters of the funding scope i.e. does not offer sufficient benefit to Parkes township. | Major | Unlikely | High | 1) Provide consolidated funding and business cases 2) Focus on benefits to townships 3) foreground the background for change (BC slide #4 combined business case ppt) 4) visuals from illsutrating supply/demand 5) develop different messages for stakeholders & FAQs | PMO, Contractor, PSC | Major | Rare | Medium | PMO | CLOSED |  | Y | Y
T7-Legal Risks | Negotiations over a pipeline easement with a local landowner sour when staff managing the negotiation mis-communicate Council’s legal position and are slow to respond to requests for information. The landowner withdraws from the negotiation forcing Council to consider compulsory acquisition. | Major | Likely | Very High | 1) Compensation offer is 'generous/reasonable' 2) Public Works manage landowners negotiation 3) Make compulsory acquisition option clear and acquisition timeframe 4) establish one point of contact throughout the negotiation process 6)PSC agrees threshold for compensation/timing with Public Works 7) Design options to avoid property acquisition (Ulmarra Bore) 8) Complete acquisitions roadmap (by Sept) 9) Start property acquisition process early (LPD pipeline) | PMO, Contractor, PSC | Major | Rare | Medium | PMO | OPEN | Line item to be reviewed prior to accessing site with PSC Comms team - Mar/Feb, - Unchaged 04.12.23, NWG risk updated - 22.01.24, No updates 03.04.24 |  | Y
T3-Social Risks | Professor Mark Howden Director of the Institute for Climate Energy and Disaster Solutions at the ANU forms an alliance with a member of the PRG, local irrigators, environmentalists, and private landowners to oppose the assumptions and outputs from Council’s Climate Change workshop. They start a Facebook page and post information that contradicts the climate change data. | Major | Possible | Very High | 1) Ensure environmental assessments are defensible, due process observed 2)Cultural heritage is transparent 3) Demonstrate low % water take from River & aquifer 4) prepare facts sheet on environmental assessment process 5) FAQs on environmental assessment approach 6) Provide CBA to townships in FSC, CTE and PSC 7) Use simple visuals/images to illustrate water volume (e.g. agricultural consumption/output) 8) Brief local Member 9) scan social media for emerging comments/position | PMO, Contractor, PSC | Major | Unlikely | High | PMO | OPEN | Risk Remains - Unchanged 04.12.23, Residual Update ( Poissible to Unlikely - 03.04.24 | Y | Y
T4-Cultural Risks inclding First Nations | Agricultural landowners near the Lachlan River join forces in opposition to Council’s proposal to increase raw water take from the Lachlan River. They observe Council staff onsite and approach surveyors and contract staff seeking detailed information about the project. Photos of Council staff are posted online, prompting residents in Forbes Shire and the Council Mayor to challenge the value of the project to residents in the Shire. | Major | Likely | Very High | 1) Prepare project card/phone number for project enquiries to centralise contact 2) Include public enquiry protocols in SWMS 3)Prepare website text as project 'one source of truth' 3) Stakeholder database reporting on a monthly basis 4)FSC briefings ongoing with Mayor and Councillors | PMO, Contractor, PSC | Major | Possible | Medium | PMO | OPEN | NWG - Updated 22.01.24, No updates - 03.04.24 | Y | Y
T3-Social Risks | Residents living within 20 metres of the works find their driveway access blocked at key times of the day during construction works and raised concerns about the proximity of works to their properties e.g. noise and light pollution from the site. | Moderate | Likely | High | 1) Ensure public enquiry protocols and notification schedules in CEMPs are applied and monitored by PMO 2) scan social media sites for emerging concerns 3) Train contractors in correct public enquiry and public management protocols (PMO). | PMO, Contractor, PSC | Moderate | Possible | Medium | PMO | OPEN | NWG - Updated 22.01.24, No updates - 03.04.24 | Y | Y
T4-Cultural Risks inclding First Nations | The Local Parkes MP from the Shooters and Fishers Party requests a meeting with the Mayor to gather more information about WSP after an enquiry from a local resident concerned about sustainable water use and the possibility that during drought conditions, local irrigators and agricultural landowners will have their water rights compromised. | Moderate | Possible | Medium | 1) Prepare a preferred approach to managing the local MP - website, briefings 2)Scan the media for MP's recent comments and positioning on the water issues 3) Consider a 'soft' option to meet with the MP for an informal discussion to scope interests and agenda (PSC Mayor) 4) Ensure all meetings are documented and key facts presented | PMO, Contractor, PSC | Moderate | Unlikely | Low | PMO | OPEN | NWG - Updated 22.01.24, No updates - 03.04.24 | Y | Y
T3-Social Risks | A local resident group in Forbes raise concerns about the volume of water to be provided to NPM (and the SAP) as part of the WSP and suggest that the Chinese ownership of the mine is contrary to local interests. | Moderate | Possible | High | 1) Share the WSP SEP with NPM Public Affairs Officer 2) Update and review current FAQs to manage question relating to NPM ownership and water volume 3) Meeting regularly with NPM management and establish the PSC position on communication risk management approach 4) Illustrate 'good citizen' and NPM's Social licence to operate (employment, job growth) 5) Monitor media for emerging issues 6) Demonstrate that the SAP and other commercial customers will precipate sustainable water use by spreading the water take across numerous water sources e.g. bores, aquifer, river and protect raw water in the Lachlan Valley | PMO, Contractor, PSC | Moderate | Rare | Medium | PMO | OPEN | NWG - Updated 22.01.24, No updates - 03.04.24 | Y | Y
T2-NWG Financial Risk | PSC not meeting SSWP Assurance Framework requirements for Approval process and hence not getting Funding: 1 PROJECT ASSURANCE GATEWAY approval and 2a FUNDING ASSURANCE GATEWAY approval | Severe | Possible | Very High | SSWP Assurance Framework understood (poster), Checklist developed with GATEWAY requirements known, Studies/ Analysis/ Reports to be structured to satisfy requirements of Assurance Framework, Early / Regular Consultation with Authorities. | PMO Support | Severe | Rare | Medium | PMO | OPEN | Risk Remains - Unchanged 04.12.23, Residual Update ( Poissible to Unlikely - 03.04.24 | Y | Y

## BBRA Coversheet
BROAD BRUSH RISK ASSESSMENT
Project: |  | Parkes Water Security Project Package 1 Funding Application + Infrastructure Construction | [5 empty] | Date: | 2023-02-23
ESTABLISH THE CONTEXT |  |  | Refer PMP Section 3.2
Key Stakeholders |  |  | Refer PMP Section 3.5.4 |  |  |  |  | Who is the Risk Owner?
Director of Infrastructure
Persons Contributing |  | Organisational Role |  | Experience with Activity (yrs) | Role in RA | Persons Contributing | Organisational Role | Experience with Activity (yrs) | Role in RA
1 | Emily Cotterill | CEO - TEF |  | Across All Tasks | TSS
2 | Graeme Stirling | Enviro Cosult / PM - TEF |  | Across All Tasks | TSS
3 | Simon Coates | PSC- Water/Quality Specialist |  | Across All Tasks | PSC
4 | Todd Trench | HH20 |  | Across All Tasks | TSS
5 | David Powell | DGP Water |  | Across All Tasks | TSS
6 | Dave Pearce | HSECQ/Construction |  | Across All Tasks | PSC
7
8
9
11
11
HAZARD IDENTIFICATION: State the technique adopted. |  |  |  | Brainstorming | Yes
|  |  |  | Reviewing Historical Data | Yes
|  |  |  | Technical Reports Used | Yes
|  |  |  | Other (specify) à | Standards used to updates
Coversheet to be circulated with Register & Treatment Plan for Sign-off by ALL Participants